## Task Board
Team Task Board - 2026-09-28 (times are estimates, not promises)
Order | Task | Assigned to | Status | Starts | Estimated finish (Miami time) | Waiting on | Where the result lands
1 | Fix the night engine: rebuild the inbox poller, check heartbeat, write 2 result files (PASTE-D-063) | Desktop (Jorge-PC) | WAITING - paste not yet received by Jorge-PC | When pasted | About 15 min after paste | Jorge pastes PASTE-D-063 into Jorge-PC | VTES-Outbox: PASTE-D-062-RESULT.txt, EXECUTOR-STATUS.txt
2 | Wally lead list: group the 1,912 unsafe-structure owners by property type and lien status (TRK-2026-9224) | Desktop (Jorge-PC) | QUEUED | After task 1 | Tomorrow 7:00 AM | Task 1 | VTES-Outbox, one file per group
3 | Cash collection: match each invoice on the spine to any payment found in mail (read-only) | Desktop (Jorge-PC) | QUEUED | After task 2 | Tomorrow 7:00 AM | Task 1 | VTES-Outbox
4 | Filler: OCR PDFs already inside a 01-JOBS TRK folder (Queue A only) | Desktop (Jorge-PC) | QUEUED | If 2 and 3 finish early | Runs until 7:00 AM | Task 1 | Sidecar files next to each PDF
5 | Night report with 'X of N' for every item | Desktop (Jorge-PC) | QUEUED | End of night | Tomorrow 7:00 AM | Task 1 | VTES-Outbox: NIGHT-REPORT_<date>.md
6 | Check Drive for task 1's two result files and confirm the poller is writing | Cloud | SCHEDULED | 7:31 PM tonight | 7:35 PM tonight | Task 1 | OPEN-ITEMS.md; one line to Jorge only if needed
7 | Watchdog: heartbeat, unacknowledged jobs, stale monitors | Cowork | RUNNING - every 4 hours | 7:14 PM tonight | Recurring | None | MY-DESK: WATCHDOG-LATEST.md; email only on new issues
8 | CDM tax-credit model build (84% complete) | Cowork | RUNNING - 5 runs a day | 9:13 PM tonight | Waits on owner word 'CDM: GO' | Jorge: CDM GO or hold | MY-DESK: CDM_PROGRESS.md
9 | Plaud recordings to Drive transcripts | Cowork | RUNNING - daily | Tomorrow 7:11 AM | Tomorrow 7:15 AM | None | Drive: PLAUD-TRANSCRIPTS
10 | Weekday business-inbox triage | Cowork | RUNNING - weekdays | Tomorrow 7:38 AM | Tomorrow 7:45 AM | None | Message to Jorge
11 | Morning report | Cloud | SCHEDULED - overnight hourly | Midnight to 6 AM | Tomorrow 8:00 AM | Desktop night results | Repo: MORNING-REPORT_<date>.md
12 | Plaza of Bal Harbour progress report draft (last run FAILED 9/23) | Cowork | AT RISK | Wed 9/30 7:02 AM | Wed 9/30 7:30 AM | Routine must not fail again | Gmail Drafts (Jorge sends)
13 | Code-enforcement lien lists: 50 homes + 50 commercial, county permit match, 2 CSVs | Cowork (proposed) | NOT STARTED - not yet assigned | After Jorge says yes | About 2 days after start | Jorge: yes to assign; vendor test send is RED | Drive: 2 CSV files
14 | Miami-Dade Unit 29 rework upload (C2026170181) | Desktop (Jorge-PC) | ON HOLD | After Jorge confirms | Same day as confirmation | Another session is already on this invoice | Stops before Send for Jorge
15 | Codex backup executor | Codex | IDLE - installed, no tasks | After Jorge's one sign-in click | n/a | Jorge: sign in on desktop shortcut | n/a
16 | Grok | Grok | NO TASKS - no connection to this system | n/a | n/a | n/a | n/a
17 | 17 owner gates (top 3 free 25 jobs: REG-0001, REG-0002, REG-0004) | Jorge | WAITING ON OWNER | Any time | n/a | None | TEAM-DEPLOYMENT-PLAN_2026-09-28.md Section G
#JorgeValdes #task-board - TRK number pending from the registry - built by Cloud from OPEN-ITEMS.md, TEAM-DEPLOYMENT-PLAN_2026-09-28.md and the live routine list